## Sheet1
LMS-> Learning management system

Feature List

Admin Panel => 30-35 days
-->Log In/Out
-->Admin Dashboard
-->Add New Subject
-->Add New Class
-->Add New Teacher
-->Edit Teacher
-->Add New Student
-->Edit Student
-->Create and update roles
-->Createand update permissions
-->Assign permssions to roles and roles assign to users
-->User management:-
-->It allows you to add and edit users, add their roles.
-->Course management:-
-->It delivers learning materials to the learners who need them.
-->The LMS can issue certificates of completion for professional certifications.
-->Reports:- Generate different type of reports
--> Document Uploades:- admin can upload documents related to students and teachers
--> Admin can manage the content
-->Create terms and conditions
-->Send email and SMS Notification
-->Admin can set time for classes
-->Admin can see student attendance

Management Panel:- 15-20 days
-->Log In/Out
-->Panel will show according to assign roles.
-->User and Role Management:-
-->Created and manage user accounts(teachers, students)
-->Assign roles and permissions(admin, teacher, student etc)
-->Courese Management:-
-->Add, update and organize courses
-->Manage course categories and tags
-->Management can active and deactive account(teacher, student)
-->Management to give task to teachers

Teacher => 17-22 days
-->Log In/Out
-->Course creation and management:-
-->Create, edit, and delete courses
-->set course details (title, description, duration, etc.)
-->Upload course materials(lectures, etc)
-->Define prerequisites for courses
-->Content Management:-
-->Upload and organize course content(documents, etc)
-->Set conttent accessibility (public, private, restricted)
-->Communication and collaboration:-
-->Messaging system for teacher-student communication
-->Messaging system for teacher-management communication
--> Teacher provide Online Classes
-->Teacher can set their calendar for availability
-->Teachers can give task to students
Student => 17-22 days
-->Log In/Out
-->View course certificates
-->post query to teacher
-->Watch uploaded video of class
-->Course Enrollment:-
-->Browse available courses
-->Register for courses
-->View enrolled courses and upcoming sessions
-->Content Access:-
-->Access course materials and resources
-->View lectures and supplementary content
-->Download course materials
-->Payment for the courses
-->Communication:-
-->Communicate with teachers
-->Receive notifications and updates related to courses

Total Estimate time:- 79-94 working days (without API)
Total Estimate for API:- 35-45(days) working days
Design in html:- 7 days working days
Design in react:- 22-25 working days